## ItemMaster
item_id | item_name | item_level | item_type | category | critical_flag | unit | supplier | notes
CLUSTER_TRAIN_001 | Training Cluster Batch 001 | 0 | CLUSTER | Deployment | Y | batch | Internal | Priority-1 training rollout
CLUSTER_INFER_002 | Inference Cluster Batch 002 | 0 | CLUSTER | Deployment | Y | batch | Internal | Priority-2 inference rollout
SERVER_H100_8GPU | 8-GPU H100 Server Node | 1 | SERVER | Server | Y | server | ODM_A | 1 server requires 8 GPUs
GPU_H100 | NVIDIA H100 GPU | 2 | COMPONENT | GPU | Y | card | GPU_VENDOR | Primary compute bottleneck
CPU_XEON | Intel Xeon CPU | 2 | COMPONENT | CPU | Y | cpu | CPU_VENDOR | 2 CPUs per server
NIC_IB_400G | 400G InfiniBand NIC | 2 | COMPONENT | NIC | Y | card | NET_VENDOR | 1 NIC per server
MEM_64G | 64GB DDR5 Memory DIMM | 2 | COMPONENT | MEMORY | N | module | MEM_VENDOR | 16 DIMMs per server

## DemandPlan
date | deployment_batch | program_name | priority | item_id | requested_servers | business_context
2026-03-21 | DEPLOY-20260321-01 | Foundation Model Training | 1 | CLUSTER_TRAIN_001 | 20 | Need 20 training servers
2026-03-24 | DEPLOY-20260324-01 | Foundation Model Training | 1 | CLUSTER_TRAIN_001 | 30 | Scale-up wave
2026-03-26 | DEPLOY-20260326-01 | Online Inference Expansion | 2 | CLUSTER_INFER_002 | 12 | Inference pod deployment
2026-03-28 | DEPLOY-20260328-01 | Online Inference Expansion | 2 | CLUSTER_INFER_002 | 18 | Quarter-end ramp

## BOM_MultiLevel
parent_item | child_item | qty_per_parent | lead_time_days | level_from | level_to | is_critical_path | notes
CLUSTER_TRAIN_001 | SERVER_H100_8GPU | 20 | 7 | 0 | 1 | Y | Batch 1 baseline training cluster
CLUSTER_INFER_002 | SERVER_H100_8GPU | 12 | 7 | 0 | 1 | Y | Inference cluster deployment
SERVER_H100_8GPU | GPU_H100 | 8 | 21 | 1 | 2 | Y | GPU bottleneck component
SERVER_H100_8GPU | CPU_XEON | 2 | 14 | 1 | 2 | Y | Dual-socket server
SERVER_H100_8GPU | NIC_IB_400G | 1 | 10 | 1 | 2 | Y | Network critical for cluster bring-up
SERVER_H100_8GPU | MEM_64G | 16 | 7 | 1 | 2 | N | Memory DIMMs

## SupplyCommit
date | item_id | committed_qty | supplier | PO | notes
2026-03-21 | GPU_H100 | 80 | GPU_VENDOR | PO-GPU-001 | Only partial allocation received
2026-03-24 | GPU_H100 | 120 | GPU_VENDOR | PO-GPU-002 | Second drop still below need
2026-03-27 | GPU_H100 | 40 | GPU_VENDOR | PO-GPU-003 | Possible delay
2026-03-20 | CPU_XEON | 40 | CPU_VENDOR | PO-CPU-001 | Initial CPU lot
2026-03-24 | CPU_XEON | 60 | CPU_VENDOR | PO-CPU-002 | Second CPU lot
2026-03-20 | NIC_IB_400G | 20 | NET_VENDOR | PO-NIC-001 | First NIC wave
2026-03-26 | NIC_IB_400G | 20 | NET_VENDOR | PO-NIC-002 | Second NIC wave
2026-03-19 | MEM_64G | 320 | MEM_VENDOR | PO-MEM-001 | Memory arrives early
2026-03-25 | MEM_64G | 320 | MEM_VENDOR | PO-MEM-002 | Memory top-up

## OpeningStock
item_id | opening_qty | as_of_date | location | notes
GPU_H100 | 16 | 2026-03-20 | DC-A | Low GPU buffer at start
CPU_XEON | 20 | 2026-03-20 | DC-A | Some CPU stock on hand
NIC_IB_400G | 8 | 2026-03-20 | DC-A | Network cards limited
MEM_64G | 128 | 2026-03-20 | DC-A | Memory less constrained